## SUBSTANTIAL
GBV Action Plan Outilne for SUBSTANTIAL risks levels projects |  | UGANDA CLIMATE SMART AGRICULTURAL TRANSFORMATION PROJECT (P173296)
Intention | Implementation | [5 empty] | Impact
Area of focus | Key mitigation measures | Key mitigation action steps | Responsible party | Date to begin | Date Due | Funding | Target | Responsible for monitoring | Supporting measure | Progress status | Progress Notes
PEOPLE | 1.1. Develop Code of conduct and/or Behavioural Standards for project personnel | Develop Code of conduct for project personnel and workers | SSDO | 2025-11-01 | 2026-01-01 |  | Code of conduct developed and available in appropriate languages | NPC | Code of Conduct document and translated versions
|  | Review the Behavioural Standards applicable to the civil servants that will be engaged with the project to ensure explicit prohibition of SEA/SH and sanctions in case of non-compliance | SSDO | 2025-11-01 | 2026-01-01 |  | BS ensure explicit prohibition of SEA/SH and include sanctions | NPC | Code of Conduct/BS document and translated versions
|  | Monitor the implementation of the Code of conduct/Behavioural standards | SSDO | 2026-04-01 | 2027-12-01 | 20000000 | All project personnel have received a training and have signed the Code of conduct/Behavioural Standards | NPC | All project personnel have received a training and have signed the Code of conduct
| 1.2 Develop and implement a training plan targeting all categories of project personnels and workers | Mobilize expertise to ensure that project related training is of quality, survivor-centered | SSDO | 2025-12-01 | 2026-01-01 | 10000000 | Technical assistance mobilized and hired to deliver SEA/SH related trainings | NPC | Short training report presenting an analysis of trainings' sex-disaggregated data and achievements
|  | Add specific language and outline SEA/SH requirements and expectations in bid documents and contracts | SSDO | 2025-08-01 | 2026-06-01 |  | Contracts with consultants/contractors include SEA/SH requirements and expectations in trainings | SSDO/NPC | Contracts with consultants/contractors highlitghting SEA/SH requirements
|  | Develop training materials on the prohibition of SEA/SH and related Code of conduct sanctions, on project-related SEA/SH risks and on the SEA/SH GM procedures. | SSDO | 2026-02-01 | 2026-02-01 | 30000000 | Training materials developed and regulalry reviewed | NPC | Training materials and updates
|  | Develop a training plan (inc. refresher/on-the-job training/awareness activities) with training/sensitization solutions for each category of project personnel and workers | SSDO | 2025-12-01 | 2025-12-01 | 5000000 | Training plan with training activities, roles & respons., targets, calendar, budget developed | NPC | Training Plan document
|  | Train all project personnel and workers before they start activities | Service provider | 2026-03-01 | 2026-04-01 | 260000000 | All project personnel have completed a training on SEA/SH risks and mitigation measures | NPC | List of project personnel trained on SEA/SH risks and mitigating measures
|  | Conduct refresher- or on-the-job training/awareness as part of project personnel, workers and civil servants ongoing training | Service provider | 2026-07-01 | 2026-08-01 | 198000000 | All project personnel have completed a refresher or on-the-job training/awareness on SEA/SH risks and mitigation measures in accordance with the training plan | NPC | List of project personnel who participated in SEA/SH risks and mitigating measures refresher or on-the-job training/awareness
|  | Monitor the rollout of the training plan | SSDO | 2026-04-01 | 2027-12-01 | 180000000 | All project personnel demonstrate awareness of project-related SEA/SH risks, of the prohibition of SEA/SH and related Code of conduct sanctions, and have necessary knowledge about the SEA/SH GM procedures. | NPC | Short training report presenting an analysis of trainings' sex-disaggregated data and achievements
| 1.3 Develop and implement a community awareness plan targetting various targeted community' groups | Mobilize expertise to ensure that project related awareness raising is of quality and survivor-centered | SSDO | 2026-02-01 | 2026-02-01 | 10000000 | Technical assistance mobilized and hired to deliver SEA/SH related trainings | NPC | ToRs for TA
|  | Add specific language and outline SEA/SH requirements and expectations in bid documents and contracts | SSDO | 2025-12-01 | 2025-12-01 |  | Contracts with consultants/contractors include SEA/SH requirements and expectations in awareness raising | DCDO/Contractor | Contracts with consultants/contractors highlitghting SEA/SH requirements
|  | Develop and review awareness materials, messages, IEC, etc. regularly, based on community’s feedbacks, consultations and evolving understanding of risks | SSDO | 2026-03-01 | 2026-04-01 | 10000000 | Awareness raising material regulalry reviewed and maintained up-to-date | Contractor | Awareness raising material and updates
|  | Develop plan for community awareness activities | SSDO | 2025-11-01 | 2025-12-01 | 3000000 | Training plan with training activities, roles & respons., targets, calendar, budget developed | NPC | Training Plan document
|  | Monitor the rollout of the community awareness plan | SSDO | 2026-05-01 | 2027-12-01 | 90000000 | Community members who participated in community awareness activities demonstrate awareness of project-related SEA/SH risks, of the prohibition of SEA/SH and related Code of conduct sanctions, and have necessary knowledge about the SEA/SH GM procedures. | DCDO/Contractor | Short community awareness activities report presenting an analysis of activities' sex and age disaggregated data and achievements
PLACES | 2.1 Develop and implement risks mitigation measures prior construction site work | Equip the construction site with separate, secure, and easily accessible facilities for both women and men working on the site. | Contractor | Qtr1 FY 2026/27 |  | BoQs | All construction sites equipped with separate, secure, and easily accessible facilities for women and men. | Contractor | Construction site plans to ensure that separate facilities for men and women are included in the design; on-site inspections prior construction work starts to verify the presence and adequcy of security measures in place (such as locks on doors, and proper lighting)
|  | Ensure that changing rooms and/or toilets are located in separate and well-lit areas, and can be locked from the inside. | Contractor | Qtr1 FY 2026/28 |  | BoQs | Changing rooms and/or toilets located in separate and well-lit areas and that can be ocked from the inside are installed in all construction sites | Contractor | Construction site plans to ensure that separate facilities for men and women are included in the design; on-site inspections prior construction work starts to verify the presence and adequacy of security measures in place (such as locks on doors, and proper lighting)
|  | Visibly install signs in appropriate language(s) around the project site (if applicable) indicating to workers and the local population that acts of Sexual Exploitation and Abuse/Harassment (EAS/HS) are prohibited on this site. | Contractor | Qtr1 FY 2026/29 |  | BoQs | All construction sites with signs indicating to workers and the local population the prohibition of Sexual Exploitation and Abuse (EAS) and Harassment (HS). | Contractor | On-site inspections prior construction work starts to verify the presence and adequacy of signs in place informing about the prohibition of SEAH.
|  | Ensure that public spaces around the project site are well-lit. | Contractor | Qtr1 FY 2026/30 |  | BoQs | Litghting system in place in the project construction site adjacent areas | Contractor | On-site inspections prior construction work starts to verify the presence and adequacy of lighting in the project construction site adjacent areas.
|  | Add specific language and outline SEA/SH requirements and expectations in bid documents and contracts | SSDO | 2025-08-01 | 2025-10-01 |  | Contracts with consultants/contractors include SEA/SH requirements and expectations in awareness raising | SSDO/NPC | Contracts with consultants/contractors highlitghting SEA/SH requirements
SERVICES | 3.1 Map GBV service providers and referral pathways in all areas of project implementation to be integrated in training and awareness materials, as well as in the GM protocols | Identify existing services mapping in project implementation area | Service providers/ DCDOs | 2026-01-01 | 2026-02-01 | 10000000 | Desk review inc. collection of available services mapping completed | SSDO/NPC | Brief analysis of available GBV services mapping and data annexed
|  | Identify existing localized referral protocols and pathways | Service providers/ DCDOs | 2026-01-01 | 2026-02-01 | 10000000 | Localized referral protocols and pathways are integrated in the SEA/SH GM manual inc. forms for safe and ethical referrals of SEA/SH survivors to GBV services | SSDO/NPC | SEA/SH GM manual and annexes
|  | Develop if needed TOR and methodology for mapping of services and referral pathways | SSDOs | 2025-12-01 | 2026-01-01 |  | ToRs for GBV services mapping developed | SSDO | ToRs for GBV services mapping
|  | Carry out the mapping | Service provider/DCDOs | 2026-01-01 | 2026-02-01 | 10000000 | GBV services mapping completed and accessible | SSDO | GBV services mapping results
|  | Regulalry update the services mapping and the referral pathways | SSDO/DCDOs | Qtr3 FY 2024/25 | Qtr3 FY 2025/27 |  | GBV services mapping maintained up to date according to a regular timeframe (e.g. once a year) | SSDO | GBV services mapping updates
| 3.2 Recruit GBV services providers to faciliate access to timely, safe and confidential services for survivors in areas where these services are unavailable | Develop TOR and recruit a GBV services providers | SSDO | 2026-01-01 | 2026-01-01 | 3000000 | Technical assistance mobilized and recruited to facilitate timely, safe and confidential acess to GBV services for SEA/SH survivors | SSDO | ToRs for GBV services providers and contract arrangements
|  | Facilitate coordination with project stakeholders responsible for survivor's timely, safe and confidential referral to GBV services | SSDO | Continous | Continous | 20000000 | All project personnel responsible for survivor's timely, safe and confidential referral to GBV services demonstrate awareness of how to liaise/coordinate with GBV services providers recruited by the project in areas where these services are not available | SSDO | Short training report presenting an analysis of trainings' sex-disaggregated data and achievements
|  | Facilitate coordination with project stakeholders responsible for survivor's timely, safe and confidential referral to GBV services | SSDO | Continous | Continous | 20000000 | All project personnel responsible for survivor's timely, safe and confidential referral to GBV services demonstrate awareness of how to liaise/coordinate with GBV services providers recruited by the project in areas where these services are not available | SSDO | Short training report presenting an analysis of trainings' sex-disaggregated data and achievements
SYSTEMS | 4.1 Set up the GM as the response and management protocol to SEA/SH and GBV cases | Mobilize expertise as needed to provide technical assistance to the operationalization of the SEA/SH sensitive GM | SSDO | 2025-12-01 | 2025-12-01 | 15000000 | Technical assistance mobilized and hired to deliver SEA/SH risks mitigating measures and GM training | SSDO | ToRs for TA
|  | Develop survivor-centered SOPs to receive, manage and respond to SEA/SH complaints including the administrative investigation, and ensure that intake forms, referral protocols forms, and informations sharing tools are available as Annexes to the SEA/SH sensitive GM manual. | Service providers/ DCDOs | 2025-12-01 | 2026-01-01 | 30000000 | SEA/SH sensitive GM manual developed inc. annexes to support each stages of grievance management, intake forms, referral protocols forms, and information sharing tools | SSDO | SEA/SH GM manual and annexes
|  | Develop training plan for all stakeholders involved in management of SEA/SH complaints | SSDO | 2025-12-01 | 2025-01-01 | 10000000 | Training plan with training activities, roles & respons., targets, calendar, budget developed | SSDO | Training Plan document
|  | Carry out training on survivor-centered SOPs and GM functioning to GM operators and other relevant stakeholders involved in the GM management | SSDO | 2026-01-01 | 2025-02-01 | 130000000 | Training plan targets achieved | SSDO | Brief analysis of trainings' sex-disaggregated data and achievements available
|  | Roll out SEA/SH sensitive GM | SSDO | 2026-02-01 | 2025-02-01 | 60000000 | SEA/SH sensitive GM is operational across all areas of project implementation | SSDO | Short narrative outilnes SEA community-based complaint mechanisms at various geographical/administrative levels of the project implementation, and explain their role in the management of SEA complaints.
|  | Monitor the SEA/SH GM rollout | SSDO | 2026-02-01 | 2025-04-01 | 40000000 | SEA/SH survivors whose case was disclosed and reported through the project SEA/SH GM receive timely survivor centered assistance | SSDO | Case narrative report(s) with key non-identifiable data points as per the World Bank policy
| GRAND TOTAL |  |  |  |  | 1174000000